## Tasks
|  |  |  | 2010 | [6 empty] | 2011 | [11 empty] | 2012
Task | Who | Notes | Deadline | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April | May
Essays: talk to Seaside about Council | MW |  |  | C
Essays: talk to John N re NU celebration | JH |  |  | C
Publishing: interview colleagues re publishing experience | JH |  |  | C
Essays: Draft Save the Date letter | MW |  |  |  | C | x
Essays: Draft Call for Essays | MW |  |  |  | C | x
Essays: talk to Florida folks re NU celebration | JH |  |  |  | C
Essays: contact founders to invite to event, request essays | MW / JH |  |  |  | C
Places: Draft Call for Cases | MW |  |  |  | C
Elements: Draft Call for Examples | MW |  |  |  | C
Publishing: clarify roles for Mike/Jen | JH / MW |  |  |  | c
Publishing: develop layout framework for all sections | MW |  |  |  | p | x | x
Publishing: draft book proposal | JH |  |  |  | p
Publishing: draft sample case: Kentlands | MW |  |  |  | p
Essays: update to Frank Starkey for Seaside Board | MW |  |  |  | x | C
Essays: Idenitfy critics | JH | ask Dan S, E Talen, B Brown, listservs - JH sent email to select group 8/20 |  |  | x | C
Essays: Set up call to discuss Seaside event | JH | JH, MW, Chuck, Natalie, TCRPC - Diane Hodel, someone fr CNU, Frank Starkey - JH sent email to Chuck 8/20 to set up |  |  | x | C
Places: Find how to get orthos | JH | USGS seems best source, but exact locations may be out of date |  |  | x | p |  | p
Essays: draft grant proposal budget | MW |  | 2010-09-15 |  | x | x | C
Essays: draft grant proposal text | JH |  | 2010-09-15 |  | x | x | C
Essays: check on getting CNU I tapes digitized | MW |  |  |  | x
Places: Get Google maps for list | JH |  |  |  | x
Places: pull together graphic design examples we each like | MW / JH |  |  |  | x
Publishing: contact publishers | JH |  |  |  | x
Marketing: draft and submit Madison session idea online | JH |  |  |  | x | c
Essays: Send Save the Date letter | MW |  |  |  |  | x | c
Publishing: create image release form | JH |  |  |  |  | x
Publishing: set up file sharing site for case and details submissions | JH/MW | www.dropbox.com? |  |  |  | x |  | p
Marketing: talk to Dhiru about Madison session idea | MW |  |  |  |  | x
Essays: contact Chris re video recording for Seaside event | MW | [5 empty] | p
Essays: talk to Frank about options for housing at Seaside | MW | [5 empty] | p
Publishing: talk to Dhiru about how he produced his graphics | MW | [5 empty] | p
Essays: talk to Chuck and others to finalize event agenda | JH | [5 empty] | p
Essays: Issue Call for Essays | MW | Are we asking speakers to pay their own way? Length for essays? | 2010-09-15 |  |  |  | c
Places: Issue Call for Cases | [6 empty] | x
Elements: Issue Call for Examples | [6 empty] | x
Essays: contact Richard Oram re funding for Seaside event | JH |  | 2010-10-15 |  |  |  | x
Essays: advertise event |  | Seaside / CNU FL handling |  |  |  |  | x | x | x | x
Places: Deadline for Case submission |  |  | 2010-11-01 | [5 empty] | x
Places: Format draft of case chapter |  | send with reminder for essays | 2010-12-01 | [5 empty] | x
Places: Finalize case selection | [9 empty] | x
Essays: Reminder for Essays |  | include draft of places under consideration | 2010-12-01 | [6 empty] | x
Essays: pre-event deadline for essays |  |  | 2010-12-31 | [6 empty] | x
Places: Secure additional images needed | [9 empty] | x | x
Places: Touch up, crop photos | [9 empty] | x | x
Elements: Deadline for Example submission |  |  | 2010-02-15 | [6 empty] | x | x | x
Marketing: CNU poll of TNDs with best lessons | [10 empty] | x
Places: Interview designers/developers | [10 empty] | x | x
Places: Draft case text | [10 empty] | x | x | x
Places: Create figure-ground drawings | [10 empty] | x | x
Essays: Review Essays - Create Program of Topics | MW / JH | [9 empty] | x
Essays: Founders Council (1/27-28/11): Kick off the 30/20 celebration |  |  | 1/27-28/11 | [7 empty] | x
Essays: Transcribe notes from Seaside event | [11 empty] | x
Essays: deadline for revised essays |  |  | 2011-02-15 | [8 empty] | x
Elements: Layout Example section | [11 empty] | x | x | x
Essays: JH / MW edit essays | MW / JH | [11 empty] | x
Places: Layout Case Section | [12 empty] | x | x
Essays: Layout essay section |  | headshots, photos of Founders at key events | [11 empty] | x
Publishing: first draft available |  |  | 2011-04-15 | [10 empty] | x
Marketing: CNU 19 |  | session where the Founders and critics debate the essays? | [12 empty] | x
Marketing: CNU monthly highlight of influential TND | [14 empty] | x | x | x | x | x | x | x | x | x | x | x | x
Publishing: book ready for print |  |  | 2011-12-15 | [18 empty] | x
Marketing: book blog? | [21 empty] | x | x | x | x | x | x
Marketing: work with publicist? | [21 empty] | x | x | x | x | x | x
Publishing: CNU 20: culmination of 30/20 celebration; book available | [26 empty] | x
Marketing: iphone app to find NU projects
Marketing: ways for people to upload and populate iphone app

## Places
[8 empty] | Scale: |  |  | Type: |  |  |  |  | Affordable Housing: |  |  |  | Tools: |  |  |  | Other Significance:
Project | Lead Design Firm | Lead Developer/ Town Founder | City | State | Weblinks | Notes | Categories of Significance | Region / Metropolis | Neighborhood (incl. Town Center, Hamlet) | Corridor | Greenfield | Brownfield | Greyfield | Suburban Retrofit | Infill | Subsidy | HOPE VI / CHOICE | Public Housing | Affordable Market Rate | Pattern Book | Private Code | Public Code | Town Architect | Production Builders | Corporate Acceptance | Sustainability | Modern Architecture | Traditional Architecture | Agriculture | Rural/Hamlet | Transit | historic preservation
Addison Circle | RTKL Associates | Post Properties | Addison | TX |  |  | neighborhood / infill / modern architecture / transit / |  | x | [5 empty] | x | [11 empty] | x |  |  |  | x
Alys Beach | DPZ |  | Walton County | FL | http://www.dpz.com/ http://www.alysbeach.com/ | -continues 30A series -stunning architecture -houses fronting on permeable walks -significant storm zone fortification | neighborhood / greenfield / pattern book / town architect / sustainability / modern architecture / |  | x |  | x | [8 empty] | x |  |  | x |  |  | x | x
Atlantic Station |  |  | Atlanta | GA |  | -large-scale urban redevelopment of brownfield -less NIMBY b/c brownield had been defunct for long time -mainstream mid-level corporate tenants -transit -scale of architecture is too large, but typical for Atlanta -includes high-rise -shuttle bus to Marta | neighborhood / brownfield / production builders / corporate acceptance / transit / |  | x |  |  | x | [11 empty] | x | x | [5 empty] | x
Baldwin Park | Torti Gallas and Partners, Inc. with SOM |  | Orlando | FL |  | -production houses, chain retail tamed, schools close to affordable housing, great successful multi-family, beautiful natural features, commercial working well, big, successful | production builders / | [16 empty] | x
Baxter Village | UDA |  | Fort Mill | SC | http://www.villageofbaxter.com/CmImageDir/28_news_1283260561.pdf | -good example of how NU can effectively reach a lower-middle class to upper-middle class budget -success of the commercial component
Belmar |  | Continuum Partners | Lakewood | CO | In | on-site construction and demolition debris recycling plant | neighborhood / suburban retrofit / |  |  |  | x | [5 empty] | x | [16 empty] | neighborhood / suburban retrofit / | neighborhood / | suburban retrofit /
Bethesda Row | Cooper Carry | Federal Realty Investment Trust | Bethesda | MD | http://www.coopercarry.com/ | -added urban center to bedroom suburb -mainstream corporate tenants -metro was catalyst -block-by-block phasing strategy | neighborhood / infill / production builders / corporate acceptance / transit / |  | x | [5 empty] | x | [8 empty] | x | x | [5 empty] | x
Celebration | Cooper, Robertson & Partners with Robert A.M. Stern Architects and pattern book by Urban Design Associates (UDA) | Walt Disney Company | Celebration | FL |  | -first large TND with production builders -Disney brought major media attention -part of FL panhandle series | neighborhood / greenfield / pattern book / production builders / corporate acceptance / |  | x |  | x | [8 empty] | x |  |  |  | x | x
Columbia Pike | Dover, Kohl & Partners |  | Arlington County | VA | http://www.doverkohl.com/ http://www.arlnow.com/2013/08/27/county‐gives‐preview‐of-arlington‐mill-community‐center/ http://www.carfreediet.com/pages/arlingtons-urban-villages/columbia‐pike/ http://www.columbiapikeva.us/ http://www.columbia-­‐pike.org/ http://greatergreaterwashington.org/tag/Columbia+Pike/ | -corridor redevelopment governed by form-based code -incremental -challenged by lack of change in public frontage | corridor / infill / public code / |  |  | x |  |  |  |  | x | [6 empty] | x
Del Mar Station | Moule & Polyzoides, Architects and Urbanists | Urban Partners LLC and Archstone-Smith | Pasadena | CA |  | network of public plazas, paseos and private courtyards / former Santa Fe depot that stood on the site was moved away during construction and then returned | infill / transit / | [7 empty] | x | [15 empty] | x
Diggs Town | UDA with CMSS Architects |  | Norfolk | VA | http://www.urbandesignassociates.com/ | -public housing redevelopment -"privatization" of open space - associating with particular units - improved care and safety -added porches to existing brick boxes | neighborhood / infill / public housing / |  | x | [5 empty] | x |  |  | x
East Beach | DPZ / UDA | Norfolk Redevelopment Housing Agency | Norfolk | VA | <http://www.eastbeachnorfolk.com/pdf/news/ReinventingTradition.pdf> <http://www.nrha.us/printpdf/147> <http://www.tndtownpaper.com/Volume8/influential_neighbor.htm> <http://www.eastbeachnorfolk.com/pdf/news/DuanyDesigns.pdf>. <http://eastbeachnorfolk.com.s11994.gridserver.com/news/documents/CNUAward2011.pdf>. <http://www.norfolk.gov/DocumentCenter/View/1646> <http://www.norfolk.gov/DocumentCenter/View/1645> <http://www.asbpa.org/pdfs/EastBeachRelease.pdf> <https://www.cnu.org/resources/projects/east-beach-2011> | Dramatic redevelopment of deteriorated World War II multi-family housing into new traditional neighborhood that showed New Urbanist principles could work in large-scale urban infill. DPZ masterplan; UDA pattern book | neighborhood / infill / |  | x | [5 empty] | x
Envison Utah, with Daybreak | Calthorpe Associates |  |  | Utah | http://www.calthorpe.com/ http://www.daybreakutah.com/property/oleander/ http://www.utahprojects.info/Project/Details/122/SoDa-Row | -large regional planning effort using scenario planning -led to FBC efforts and TND development | region / | x | [13 empty] | x
Glenwood Park | Tunnell-Spangler-Walsh / DKP | Green Street Properties (Charles Brewer) | Atlanta | GA | http://www.doverkohl.com/files/pdf/Glenwood%20Park_low%20res.pdf http://fuquadevelopment.com/projects http://www.metrojacksonville.com/article/2012-may-revitalizing-neighborhoods-atlantas-glenwood-park http://clatl.com/freshloaf/archives/2013/10/10/bza-to-hear-appeal-over-glenwood-park-project-rev-joe-beasley-speaks-out-against-tragically-misinformed-opponents | -transit ready - on proposed Marta beltline / traffic calming of state highway / former industrial; -good “all around” NU project in terms of demonstrating principles: it’s infill at the neighborhood scale, in a big city, eco features, diverse in housing and use, some commercial and retail, production builders | neighborhood / brownfield / infill / traditional architecture / |  | x |  |  | x |  |  | x | [12 empty] | x
Habersham | DPZ |  | Beaufort | SC | http://www.dpz.com/ | -slow incremental development with light imprint infrastructure -rural hamlet -ok plan but excellent implementation | neighborhood / greenfield / private code / sustainability / traditional architecture / rural/hamlet / |  | x |  | x | [9 empty] | x |  |  |  |  | x |  | x |  | x
Iberville Offsites | Kronberg Wall Architects | Redmellon Restoration and Development | New Orleans | LA | https://www.cnu.org/what-we-do/build-great-places/iberville-offsites | -restoration of historic houses throughout a neighborhood -affordable housing for mdoerate income -disaster recovery | neighborhood / infill / CHOICE neighborhood affordability / sustainability / traditional architecture / historic preservation |  | x | [5 empty] | x | [10 empty] | x |  | x |  |  |  | x
I’on | Dover, Kohl & Partners with Duany Plater-Zyberk & Company, DesignWorks, and Seamon Whiteside | Vince Graham | Mount Pleasant | SC |  | developer set up builders guild | neighborhood / traditional architecture / |  | x | [7 empty] | x | [10 empty] | x
Kendall | Dover, Kohl & Partners / DPZ |  | Kendall | FL | http://www.doverkohl.com/ http://www.downtowndadeland.com/siteplan.html http://www.miamitodaynews.com/news/030508/story2.shtml | -suburban retrofit of regional mall into town center -midscale corporate tenants | neighborhood / greyfield / suburban retrofit / corporate acceptance / |  | x |  |  |  | x | x | [10 empty] | x
Kentlands | DPZ | Joe Alfandre | Gaithersburg | MD | http://www.dpz.com/ | -fine scale of mix of housing types and uses -weave of big box with hidden parking to fine-grained main street -first public charrette? -long-term use of private code with town architect | neighborhood / greenfield / private code / town architect / production builders / traditional architecture / |  | x |  | x | [9 empty] | x |  | x | x |  |  |  | x
Legacy Town Center |  |  | Plano | TX |  | -a new neighborhood off the freeway; -co-location reusing big single use office park; -hotel/conference center, multi-family, retail+park/lake; -plan hard to read but works in elevation | neighborhood / suburban retrofit / |  | x |  |  |  |  | x
Mashpee Commons | Cornish Associates | Buff Chace and Douglas Storrs | Mashpee | MA | http://www.cornishlp.com/ | -suburban retrofit of regional mall | neighborhood / greyfield / suburban retrofit / private code / corporate acceptance / traditional architecture / |  | x |  |  |  | x | x | [6 empty] | x |  |  |  | x |  |  | x
Mississippi Renewal Forum | DPZ with CNU |  |  | MI | http://www.dpz.com/ | -disaster recovery effort -largest charrette ever? -smartcodes, especially in Pass Christian MS -katrina cottage (disaster relief to transition to permanent affordable housing) | region / affordable market rate / pattern book / public code / traditional architecture / | x | [10 empty] | x | x |  | x | [5 empty] | x
Mueller Airport Redevelopment | McCann Adams Studio | public private partnership between the City of Austin and Catellus Development Corporation | Austin | TX | http://www.muelleraustin.com/about/ | -700 acre development of former airport near downtown -public private partnership -mix of affordable housing and market rate housing | neighbothood (but multiple) / mix of market rate and affordable subsidy / sustainability |  | x |  |  |  | x |  | x |  |  |  | x | [6 empty] | x
New Town St. Charles | DPZ | Whittaker Homes | St. Charles | MO | http://www.dpz.com/ | -market rate affordability with production builders -stormwater retention in canals -large scale in terms of number of acres | town / greenfield / affordable market rate / private code / town architect / production builders / traditional architecture / |  |  |  | x | [7 empty] | x |  | x |  | x | x |  |  |  | x
Orenco Station | PacTrust | PacTrust | Hillsboro | OR |  | study by sociologist Bruce Podobnik found that Orenco residents use mass transit more than they did in previous neighborhoods and walk to local stores more than residents of suburban neighborhoods | neighborhood / traditional architecture / transit / |  | x | [18 empty] | x |  |  | x
Park DuValle | UDA | Louisville Metro Housing Authority | Louisville | KY | 31st Floor, Gulf Tower 707 Grant Street Pittsburgh, PA 15219 | One-third of the development’s homes are selling at the market rate, one-third are subsidized to sell at less than the market rate, and one-third are public housing. | neighborhood / HOPE VI / public housing / affordable market rate / traditional architecture / |  | x | [7 empty] | x | x | x | [8 empty] | x
Petaluma Downtown SmartCode | Hall Alminanna |  | Petaluma | CA |  | -mandatory smartcode unleashed pent-up demand that led to substantial redevelopment | neighborhood / infill / public code / |  | x | [5 empty] | x | [6 empty] | x
Pleasant Hill Transit Village (BART TOD) | Lennertz Coyle |  | Contra Costa County | CA | http://www.contracostatimes.com/ci_23696451/much-pleasant-hill-contra-costa-centre-bart-transit http://www.urbanexus.com/2011/12/19/avalaon-bay-apartments-at-contra-costa-centre-in-the-san-francisco-bay-area/ http://www.mve-institutional.com/project.php?lID=198&subgID= http://www.ccreach.org/ccc_redevelopment/ph_finaldp.cfm http://www.contracostacentre.com/ http://www.avaloncommunities.com/california/walnut-creek-apartments/avalon-walnut-creek/ | built example of TOD with commercial success | neighborhood / infill / transit / |  | x | [5 empty] | x | [15 empty] | x
Poundbury | Leon Krier |  |  | England |  |  | greenfield / sustainability / traditional architecture / | [6 empty] | x | [14 empty] | x |  | x |  | greenfield / sustainability / traditional architecture / | greenfield / |  |  | sustainability / | traditional architecture /
Prospect | DPZ | Kiki Wallace | Longmont | CO |  | -required modern architecture | neighborhood / greenfield / private code / town architect / modern architecture / traditional architecture / |  | x |  | x | [9 empty] | x |  | x |  |  |  | x | x
Rosemary Beach | DPZ | Leucadia Financial | Walton County | FL | • http://www.cnu.org/cnu-salons/2012/06/new-urbanist’s-pilgrimage-part-i-rosemary-beach • http://bettercities.net/places/placesnewurbandevelopment/rosemary-beach • http://simonandbaker.com/rosemary_beach.html • http://www.rosemarybeach.com • http://oldurbanist.blogspot.com/2011/08/successor-rosemary-beach.html http://www.rosemarybeach.com/beach_community_history.aspx • http://www.dpz.com/Practice/9507 • http://www.terrain.org/unsprawl/12/ | mostly custom houses / native landscaping, stormwater system uses pervious surface infiltration rather than piping and storage | neighborhood / greenfield / private code / town architect / sustainability / traditional architecture / |  | x |  | x | [9 empty] | x |  | x |  |  | x |  | x
Seaside | DPZ | Robert and Daryl Davis | Walton County | FL | http://www.dpz.com/ http://www.seasidefl.com/history/April2014 | -study of precedent -first charrette? due to coordination and access problems -taming 30A -how resort spreads the word - people will try new things on vacation, learn about a different way of living, and then travel home -key importance of public space - didn't privatize beach -slow, incremental development with low infrastructure costs -private urban design code that did not regulate architectural style - mix of traditional and modernist buildings -importance of nurturing local businesses and programming | neighborhood / greenfield / private code / sustainability / modern architecture / traditional architecture / |  | x |  | x | [9 empty] | x |  |  |  |  | x | x | x
Serenbe | Phillip Tabb |  | Chattahoochee Hills | GA | http://www.arch.tamu.edu/ | William Lewis Oliver, III (architectural director), and Sean J. Murphy (project landscape architect). NUN: The plan is based on “omega curves” and crossroads. The omega curves creates a linear “road side” town with a transect that is most intense at the peak of the curve and more rural moving away in either direction. The single corridor design means that houses back up to large continuous natural spaces that are preserved in perpetuity. | neighborhood / greenfield / private code / town architect / sustainability / modern architecture / traditional architecture / agriculture / rural/hamlet / |  | x |  | x | [9 empty] | x |  | x |  |  | x | x | x | x | x
The Cotton District |  | Dan Camp | Starkville | MS | https://www.cottondistrictms.com/ | -incremental infill in a small town with a university -surprising density for a small southern town -small development over time -mixed use | neighborhood / infill / incremental / historic preservation |  | x | [5 empty] | x | [12 empty] | x |  |  |  | x
The Waters | PlaceMakers LLC / Mouzon Design |  | Pike Road | AL | http://www.mouzon.com/MDZ/Home.html | good SmartCode story; mid-block greens / builder education: The Waters team hosted weekly, on‐site information sessions with local builders for the year prior to construction / NUN: As a testament to The Waters’ influence in the region, the surrounding community of Pike Road and the City of Montgomery subsequently adopted the SmartCode to guide future development. Evolutionary architecture - not copying style | neighborhood / greenfield / private code / public code / town architect / traditional architecture / |  | x |  | x | [9 empty] | x | x | x |  |  |  |  | x
And many more:
Aldea, formerly “Frijoles Village,” outside Santa Fe - Frijoles Village, a traditional neighborhood development in ¦ CNU not yet built out, but fully entitled and selling. If anyone wants to do research on how they created it in the 90s, check out Frijoles Village Development Materials, 1994-2001 ¦ New Mexico Archives Online (unm.edu) – good amount built (DPZ)
Angus Glenn, Markham (completed), Greater Toronto Area
Aria GA (DPZ)
Beachtown Galveston (DPZ)
Bermuda Village FL (DPZ)
Birkdale Village
Blatchford (20%?), Edmonton
Blount Springs (DPZ) - not fully implemented, but you might consider it
Blue water FL (DPZ)
Bois Franc (completed), Montreal
Campo Sano FL (DPZ)
Carlton Landing, OK
Cayala, http://theaestheticcity.com/
Chapelton Scotland (DPZ)
Church Hill North, Richmond, VA (Choice Neighborhood, successor to Hope VI) (Torti Gallas)
City West, Cincinnati, OH (Hope Vi) (Torti Gallas)
Civano, AZ (also book with same name on how it was developed by Stefanos and Lee Rayburn) (Moule & Polyzoides teamed with DPZ – town)
Columbia Heights, Washington, DC (maybe, or is it just an urban shopping mall?) (Torti Gallas)
Cornell, Markham (80% completed), Greater Toronto Area
Crystal City Master Plan, Arlington, VA (This plan led the selection of the site for Amazon’s HQ2 (Torti Gallas)
DownCity Providence RI (DPZ)
Downtown Birmingham MI (DPZ)
Downtown Doral FL (DPZ)
Downtown Los Angeles (Moule & Polyzoides – “recast” of existing city)
Downtown Stuart FL (DPZ)
Downtown Westminster, CO (Torti Gallas)
Eddy Street
Fairview Village, Fairview, Oregon, Bill Dennis, Bill Lennertz, Steve Coyle 1994 https://www.cnu.org/what-we-do/build-great-places/fairview-village
Ft. Belvoir Military Housing Neighborhoods, Fairfax County, VA (Torti Gallas)
Garrison Commons (completed), Calgary
Hammonds Ferry in SC (Steve Maun)
Hampstead AL (DPZ)
Hendrick Farm Canada (DPZ)
Hendrix College AR (DPZ)
Hendrix Village AR (DPZ)
King Farm, Rockville, MD (Torti Gallas)
Lakelands MD (DPZ)
Lancaster Blvd (Moule & Polyzoides – street)
Las Catalinas
Liberty Harbor North NJ (DPZ)
Lost Rabbit (DPZ)
MacKenzie Towne (completed?), Calgary
Mahogany Bay Village (Studio Sky) - this is a rescue project in Belize so it would be an unconventional choice, but accomplishes several NU goals not often implemented
Markham Centre (25% completed), Greater Toronto Area
Martin Luther King Jr. Plaza, Philadelphia, PA (Hope Vi) (Torti Gallas)
Miami21 FL (DPZ)
Middleton Hills WI (DPZ)
Mount PLeasant Village, Brampton (completed), Greater Toronto Area
Mt Laurel AL (DPZ)
New Columbia (Marcy McInelly)
Newpoint, Beaufort SC
Norton Commons KY (DPZ)
Oak Park, Oakville (80% completed), Greater Toronto Area
Old Hatfield England (DPZ)
Plan Baton Rouge LA (DPZ)
Playa Vista, Los Angeles (DPZ teamed with Moule & Polyzoides – neighborhood)
Plessis Robinson (DPZ), http://theaestheticcity.com/
Port Royal, SC
Potomac Yard is one of several in the DC area not listed; are they considered insufficiently NU?
Preserve (LRK)
Rio Nuevo, Tucson, AZ (Moule & Polyzoides – neighborhood)
Rockville Town Center (Richard Heapes)
Salishan, Tacoma, WA (Hope Vi) (Torti Gallas)
Schooner Bay (DPZ)
Schooner Bay Bahamas (DPZ)
Seabrook
Seafront Residences Philippines (DPZ)
Southern Village, Chapel Hill, NC
Southlands Canada (DPZ)
Southlands, Tsawwasen, Canada (Vancouver area), (5% complete?), (DPZ)
Storrs Center - town center for U of Conn and Town of Mansfield in CT (Steve Maun)
The Neighborhood Model, Albemarle County, VA (Torti Gallas)
Tornagrain Scotland (DPZ)
Town of Tioga west of Gainesville, FL
Trilith
Uptown Normal (Farr Associates), https://www.farrside.com/uptown-normal
Village at Niagara On The Lake: A DPZ designed TND 90% built out in Niagara On The Lake in Ontario Canada - across the river from Buffalo: http://thevillageniagara.com
Village of Cheshire NC (DPZ)
Village of Oakland Springs (studio LFA)
Village of Providence AL (DPZ)
Villebois, Wilsonville, OR. Steve Coyle assisted on the plan by Costa Pacific Architects and was town architect from 2004 to about 2019. https://www.ci.wilsonville.or.us/planning/page/villebois-concept-plan
Warwick Grove in NY (Steve Maun)
Westhaven TN (DPZ)
Westlawn, Milwaukee, WI (Hope Vi) (Torti Gallas)
Wheeler District, Oklahoma City OK
Windsor FL (DPZ)
General websites to check for info:
http://www.cnu.org/
https://www.cnu.org/resources/project-database
http://www.tndtownpaper.com/neighborhoods.htm
https://www.epa.gov/smartgrowth/examples-smart-growth-communities-and-projects